## Planner
| 2023 | 2023
| 2099 | 1063
| MODENA | SANTIAGO DE COMPOSTELA
Store Address | Centro Commerciale Grandemilia, Via Emilia Ouest 61, 41121, Modena, Italy | Centro Comercial As Cancelas. Avenida Do Camino Frances, 3. 15073. Santiago de Compostela. A Coruna, Spain
Country | Italy | Spain
Region | South | South
Development Type (New/Existing) | Shopping Centre (Existing) | Shopping Centre (Existing)
Project Type (New/Refurb/Existing) | New Store | UPSIZE
Type / Grade | 3M | 3G
Floor type | Vinyl | Ceramic
Supplier | TBC | TBC
Stage One Meeting
Project Brief Issued | N/A | 2022-07-27
Initial Visit | 2022-06-22 | 2022-08-10
Cost Check Meeting
PBM | 2022-10-26 | 2022-08-24
Lease Commence Date
Landlord / Center Handover | 2023-01-30 | 2023-02-27
Commence Works | 2023-02-08 | 2023-02-27
Shop Fit Completion Date (GC Handover) | 2023-04-21 | 2023-04-25
Retail Handover Date | 2023-05-05 | 2023-02-02
Retail Handover Time | 8:00 | 21:00
Stock Delivery Date | 2023-05-05 | 2023-02-02
Stock Delivery Time | 9:00 | 22:00
Opening date | 2023-05-04 | 2023-05-05
Project Sign Off | 2023-05-24 | 2023-05-25
Stock Order | 2023-02-10 | 2022-11-10
Duration (Days) | 87 | -24
Duration (Weeks) | 12.4286 | -3.4286
Sales area FT2 (sqft) | TBC | 627 m2
Sales area M2 (sqm) |  | 430m2
Quarter
PBM Status | BOARD APPROVED | BOARD APPROVED
Lease Signed | TBC | Yes
Asbestos Survey | TBC | N/A
Internal PM | Marco Mirra | Jose Diaz
Acquisition Manager | Giorgio Casella | Gabriele Bocci
Designer | Francesca Cipullo | Jose Andreu
QS | Clara Arenal | Andres Blarasin
Main Contractor | COGESIM | Ramon Garcia
Architect | TSE | ATLANTE
Local Technical Specialist | TSE | N/A
H&S Consultant | FRAREG | GTP
HSV |  | 2023-03-23
Signage Contractor | Innovate | Innovate
Feasibility Drawings + Shop Front Visual | 2022-07-29 | 2022-08-09
Stage 1 drawings | N/A | 2022-09-16
Stage 2 drawings | 18th Nov 23 | 2022-09-30
Technical Projects (M&E) | 2022-10-24 | 2023-01-13
Construction Pack + S&G Pack | 2023-02-08 | 2023-01-24
Landlord Submission date | TBC | N/A
Landlord/Centre Approval | TBC | N/A
Building Permit Warrant (Est. Appr. Period) | 30days | N/A
Building Permit Warrant (Latest Submission Date) | 2023-01-11 | N/A
Approval Date (Estimated) | 2023-02-08 | N/A
Hoarding permit | - | N/A
Shop Front Permit | - | N/A
Hoarding/Window artwork deadline | TBC | 2023-02-07
Artwork Approval | TBC | 2023-02-17
Hoarding / Window vinyl install date | TBC | 2023-02-27
Capex PBM | 2022-10-26 | 2022-08-24
Capex Approved | TBC | 2022-08-24
Main Tender Out | 2022-10-27 | 2023-01-13
Tender in | 2022-11-24 | 2023-01-27
Award GC (Latest date) | 2022-12-13 | 2023-02-03
PCM | 2023-01-25 | 2023-02-13
Commence Works | 2023-01-30 | 2023-02-27
SM1 | 2023-02-08 | 2023-03-07
SM2 | 2023-02-15 | 2023-03-14
SM3 | TBC | 2023-03-21
SM4 | TBC | 2023-03-28
SM5 | TBC | 2023-04-04
SM6 | TBC | 2023-04-13
SM7 | TBC | 2023-04-18
SM8 | TBC | -
SM9 | TBC | -
SM10 | TBC | -
SM11 | TBC | -
Number of AP's | TBC | TBC
Delivery of AP's (Latest) | TBC | 2023-03-31
Number of Tills | 1 Cash Desk (3 Tills) | 4 Tills (1Cash Desk)
Kiosk Type / Nr | TBC | 1WM (C&P)
Phone Line Installation (Latest) | TBC | TBC
Switch Install | TBC | TBC
Router Install | TBC | TBC
Till & Back Office PC Install | TBC | TBC
Chip & Pin Install | TBC | TBC
Multimedia / LED Walls | TBC | No
Installation date | TBC | TBC
Number Entrances | 2 | 3
Vertical Circulation (Escalators/Stirs/Lifts) | N/A | N/A
Required | - | Yes
Number of TVs | - | 4
Bracket Type (Wall or Pole) | - | Pole
Re-assessed / Wall mounted | TBC | Wall Mounted
Speaker number | TBC | TBC
DJ Point required | TBC | N/A
Type 1-2 system required | TBC | N/A
1st fix install date | TBC | TBC
2nd fix Install date | TBC | TBC
Safe Install date | TBC | TBC
Tagging Gates Install date | TBC | TBC
Multi Locks Delivery date | TBC | TBC
Lift required | N/A | N/A
Dumbwaiter(s) required | N/A | N/A
Shoe chute | NA | N/A
Escalator required | N/A | N/A
Formulas:
Italy = [Italy, row above]+20
Spain = [Spain, row above]+10

## Timeline
YEAR | COUNTRY CODE | STORE NUMBER | PROJECT NAME | FASCIA | STORE ADDRESS | COUNTRY | REGION | DEVELOPMENT TYPE (NEW/EXISTING) | PROJECT TYPE (NEW/REFURB/EXISTING) | TYPE / GRADE | FLOOR TYPE | SUPPLIER | COMMNETS | 0 | STAGE ONE MINUTE | PROJECT BRIEF ISSUD | INITIAL VISIT | COST CHECK MEETING | PBM | LEASE COMMENCE DATE | 0 | LANDLORD / CENTER HANDOVER | COMMENCE WORKS | SHOP FIT COMPLETION DATE (GC HANDOVER) | RETAIL HANDOVER DATE
| IT |  | MODENA |  | Centro Commerciale Grandemilia, Via Emilia Ouest 61, 41121, Modena, Italy | Italy | South | Shopping Centre (Existing) | New Store | 3M | Vinyl | TBC |  |  | 0 | N/A | N/A | #REF! | 2022-10-26 | 0 |  | 2023-01-30 | 2023-02-08 | 2023-04-21 | 2023-05-05
| ES |  | SANTIAGO DE COMPOSTELA |  | Centro Comercial As Cancelas. Avenida Do Camino Frances, 3. 15073. Santiago de Compostela. A Coruna, Spain | Spain | South | Shopping Centre (Existing) | UPSIZE | 3G | Ceramic | TBC |  |  | 0 | 2022-07-27 | 2022-07-27 | #REF! | 2022-08-24 | 0 |  | 2023-02-27 | 2023-02-27 | 2023-04-25 | 2023-02-02
Formulas:
STAGE ONE MINUTE = '[1]S.Planner 2023'!$F16
STAGE ONE MINUTE = '[1]S.Planner 2023'!$G16
PBM = '[1]S.Planner 2023'!$F20
PBM = '[1]S.Planner 2023'!$G20
LEASE COMMENCE DATE = '[1]S.Planner 2023'!$F21
LEASE COMMENCE DATE = '[1]S.Planner 2023'!$G21
LANDLORD / CENTER HANDOVER = '[1]S.Planner 2023'!$F23
LANDLORD / CENTER HANDOVER = '[1]S.Planner 2023'!$G23
COMMENCE WORKS = '[1]S.Planner 2023'!$F24
COMMENCE WORKS = '[1]S.Planner 2023'!$G24
SHOP FIT COMPLETION DATE (GC HANDOVER) = '[1]S.Planner 2023'!$F25
SHOP FIT COMPLETION DATE (GC HANDOVER) = '[1]S.Planner 2023'!$G25
PROJECT BRIEF ISSUD = '[1]S.Planner 2023'!$G17
INITIAL VISIT = '[1]S.Planner 2023'!$G17